## Assumptions
CharredGuard — Growth Model Assumptions
Edit the yellow cells. Growth Curve and POAM sheets recalculate from these.
Launch Date (Month 1 start) | 2026-09-01
On-Site Audit Price ($) | 500
Guided Self-Inspection Price ($) | 200
Avg Hardening Add-On Ticket ($) | 450
Hours per On-Site Audit (travel + visit + report) | 4
Hours per Guided Self-Inspection (review + report) | 1
Hours per Hardening Job (travel + materials + install) | 4
Sustainable Solo Delivery Hours / Week | 25
Weeks per Month (avg) | 4.33
Note: delivery-hour estimates and the 25 hr/wk sustainable-capacity figure are working assumptions, not measured data — adjust as real jobs give you actual timing.
Path & Profitability Inputs
Solo Part-Time Hours / Week (evenings, Paths B & C, and Path A before partner joins) | 12
Two-Person Full-Time Hours / Week (Path A, after partner joins) | 45
Partner Join Month (Path A trigger, 1-12) | 6
Audit / Self-Inspection Gross Margin (%) | 90%
Hardening Add-On Gross Margin (%) | 65%
Fixed Monthly Overhead ($) | 223
These three paths are the actual decision on the table, not just optimism levels. Path A assumes your business partner leaves their job once volume justifies it (Month 19 sets when); Path B keeps this a permanent evenings/weekends operation; Path C also stays part-time solo but drops the hardening add-on entirely, which sidesteps almost every open item in legal-risk-notes.md since there's no contractor-licensing exemption being relied on.

## Growth Curve
Year 1 Growth Curve & Solo-Capacity Check
Volume targets are from the business plan's Year-1 projection. Hours/Capacity columns are computed live from the Assumptions sheet.
Month # | Target Month | Audits | Self-Inspections | Hardening Jobs | Revenue ($) | Delivery Hours | Hours / Week | Capacity Status
1 |  | 2 | 1 | 1
2 |  | 3 | 2 | 1
3 |  | 4 | 2 | 2
4 |  | 5 | 3 | 2
5 |  | 6 | 3 | 3
6 |  | 8 | 4 | 3
7 |  | 9 | 4 | 4
8 |  | 10 | 5 | 4
9 |  | 11 | 5 | 5
10 |  | 12 | 6 | 5
11 |  | 12 | 6 | 5
12 |  | 14 | 6 | 6
TOTAL
Formulas:
Target Month = EDATE(Assumptions!$B4,[Month #]-1)

## POAM
CharredGuard — Plan of Action & Milestones (Year 1)
ID | Phase | Milestone / Action | Category | Target Timing | Owner | Depends On | Status | Success Criteria / Notes
0.0 | Phase 0 — Pre-Launch | Decide operating path: (A) partner joins full-time once volume justifies it, (B) permanent part-time evenings solo, or (C) homeowner-inspections-only solo part-time (no hardening add-on) | Planning | Before Month 1 | Matt (+ partner) | — | Not Started | Decision documented — see 'Business Model Paths' tab. Determines whether hardening-related POAM items (1.3, 2.1) and legal-risk items 1/2/5/6 are even relevant.
0.1 | Phase 0 — Pre-Launch | Form California LLC (Articles of Organization) | Legal | Before Month 1 | Matt | — | Not Started | LLC registered with CA Secretary of State
0.2 | Phase 0 — Pre-Launch | Obtain EIN + open business bank account | Financial | Before Month 1 | Matt | 0.1 | Not Started | EIN issued, account open
0.3 | Phase 0 — Pre-Launch | Bind combined GL + E&O insurance policy | Legal/Risk | Before Month 1 | Matt | 0.1 | Not Started | Policy active, ~$145/mo confirmed
0.4 | Phase 0 — Pre-Launch | Attorney review of Inspection Agreement, Minor Work Contract, Liability Waiver (Section 9 templates) | Legal | Before Month 1 | Matt + CA attorney | — | Not Started | Written sign-off before any client signs a contract
0.5 | Phase 0 — Pre-Launch | Confirm hardening-work permit requirements per target city (Carlsbad, Escondido, Fallbrook, Ramona, Coto de Caza, Silverado Canyon, etc.) | Legal/Compliance | Before Month 1 | Matt | — | Not Started | B&P §7048 exemption requires NO permit — verify per city before offering hardening add-on
0.6 | Phase 0 — Pre-Launch | Confirm marketing/signage won't count as 'holding out as a contractor' under B&P §7048 | Legal | Before Month 1 | Matt + CA attorney | — | Not Started | Flagged risk: worksite banners + hardening-focused branding could void the minor-work exemption — get explicit guidance before Phase 2 signage/marketing
0.7 | Phase 0 — Pre-Launch | Begin NFPA CWMS certification study | Certification | Before Month 1 | Matt | — | Not Started | Exam scheduled
0.8 | Phase 0 — Pre-Launch | Website live with correct pricing ($500/$200) and SoCal geography | Marketing | Before Month 1 | Matt | — | Done | Completed — charred-guard-site updated
1.1 | Phase 1 — Audit-Only Launch (M1-3) | Deliver first paid on-site audit | Ops | Month 1 | Matt | 0.1-0.4 | Not Started | First $500 invoice paid
1.2 | Phase 1 — Audit-Only Launch (M1-3) | Deliver first guided self-inspection | Ops | Month 1 | Matt | 0.1-0.4 | Not Started | First $200 invoice paid
1.3 | Phase 1 — Audit-Only Launch (M1-3) | Hold hardening add-on revenue until 0.5 and 0.6 are cleared | Legal gate | Months 1-3 | Matt | 0.5, 0.6 | Not Started | Do not sell hardening work until permit + advertising questions are resolved in writing
1.4 | Phase 1 — Audit-Only Launch (M1-3) | Reach monthly break-even (~$248 revenue covers fixed overhead) | Financial | Month 3 | Matt | 1.1, 1.2 | Not Started | See business plan §7.3
1.5 | Phase 1 — Audit-Only Launch (M1-3) | First conversation with a local independent insurance broker or realtor | B2B/Marketing | Months 1-3 | Matt | — | Not Started | Relationship opened, not necessarily signed
2.1 | Phase 2 — Hardening Launch & Marketing Scale (M4-6) | Turn on hardening add-on revenue | Ops/Legal | Month 4 | Matt | 1.3 | Not Started | Only after 0.5 and 0.6 are formally cleared
2.2 | Phase 2 — Hardening Launch & Marketing Scale (M4-6) | Launch Nextdoor Verified Sponsorship in 2-3 target ZIP codes | Marketing | Month 4 | Matt | 0.6 | Not Started | Sponsorship live
2.3 | Phase 2 — Hardening Launch & Marketing Scale (M4-6) | Deliver first HOA or Fire Safe Council presentation | Marketing | Months 4-6 | Matt | — | Not Started | Presentation delivered
2.4 | Phase 2 — Hardening Launch & Marketing Scale (M4-6) | NFPA CWMS certification achieved | Certification | Months 4-6 | Matt | 0.7 | Not Started | Trigger: add certification badge + trust stats to website
2.5 | Phase 2 — Hardening Launch & Marketing Scale (M4-6) | First capacity check-in using Growth Curve sheet | Ops | Month 6 | Matt | — | Not Started | Confirm Hours/Week is still under the sustainable threshold
3.1 | Phase 3 — Partnerships & Capacity Checkpoint (M7-9) | Signed referral agreement with 1+ insurance broker | B2B | Months 7-9 | Matt | 1.5 | Not Started | Signed agreement or MOU
3.2 | Phase 3 — Partnerships & Capacity Checkpoint (M7-9) | Formal referral relationship with 1+ real estate agent (AB-38 angle) | B2B | Months 7-9 | Matt | 1.5 | Not Started | Signed agreement or MOU
3.3 | Phase 3 — Partnerships & Capacity Checkpoint (M7-9) | Capacity decision: bring on part-time help if Growth Curve sheet shows Hours/Week over threshold | Hiring | Months 7-9 | Matt | 2.5 | Not Started | Decision documented either way — field assistant for hardening installs, or admin/VA for CRM & scheduling
3.4 | Phase 3 — Partnerships & Capacity Checkpoint (M7-9) | Add a business phone number to the site | Marketing | Months 7-9 | Matt | — | Not Started | Flagged in earlier competitive review
4.1 | Phase 4 — Scale & Year 2 Planning (M10-12) | Reassess whether hardening volume still fits the $1,000 minor-work exemption, or whether a specialty contractor license makes sense | Legal/Ops | Months 10-12 | Matt | 3.3 | Not Started | Written decision + attorney check-in if volume grew
4.2 | Phase 4 — Scale & Year 2 Planning (M10-12) | Evaluate hiring a second inspector/technician | Hiring | Months 10-12 | Matt | 3.3 | Not Started | Decision documented
4.3 | Phase 4 — Scale & Year 2 Planning (M10-12) | Full-year financials reviewed against Year-1 projections | Financial | Month 12 | Matt | — | Not Started | Actuals vs. plan variance noted
4.4 | Phase 4 — Scale & Year 2 Planning (M10-12) | Draft Year 2 plan and budget | Planning | Month 12 | Matt | 4.3 | Not Started | Year 2 document drafted

## Business Model Paths
Which Path — Partner Joins Full-Time / Part-Time Evenings / Homeowner-Only
Audits / Self / Hardening are editable per-path inputs (blue) — each path has a genuinely different volume story, not just a multiplier. Revenue, Hours/Week, and Capacity are formulas that recalc from the Assumptions tab.
|  | A — PARTNER JOINS FULL-TIME |  |  |  |  | B — PART-TIME EVENINGS (SOLO, INDEFINITELY) |  |  |  |  | C — HOMEOWNER INSPECTIONS ONLY (SOLO, PART-TIME, NO HARDENING)
Month # | Target Month | Audits | Self | Hardening | Revenue ($) | Hrs/Wk | Audits | Self | Hardening | Revenue ($) | Hrs/Wk | Audits | Self | Hardening | Revenue ($) | Hrs/Wk
1 |  | 1 | 1 | 0 |  |  | 1 | 1 | 0 |  |  | 1 | 1 | 0
2 |  | 2 | 1 | 0 |  |  | 1 | 1 | 0 |  |  | 2 | 1 | 0
3 |  | 2 | 2 | 1 |  |  | 2 | 1 | 1 |  |  | 2 | 2 | 0
4 |  | 3 | 2 | 1 |  |  | 2 | 1 | 1 |  |  | 3 | 2 | 0
5 |  | 3 | 2 | 1 |  |  | 2 | 2 | 1 |  |  | 3 | 2 | 0
6 |  | 6 | 3 | 2 |  |  | 2 | 2 | 1 |  |  | 3 | 3 | 0
7 |  | 8 | 4 | 3 |  |  | 3 | 2 | 1 |  |  | 4 | 3 | 0
8 |  | 9 | 4 | 4 |  |  | 3 | 2 | 1 |  |  | 4 | 3 | 0
9 |  | 10 | 5 | 4 |  |  | 4 | 2 | 1 |  |  | 4 | 3 | 0
10 |  | 11 | 5 | 5 |  |  | 4 | 2 | 1 |  |  | 5 | 3 | 0
11 |  | 12 | 6 | 5 |  |  | 4 | 2 | 1 |  |  | 5 | 3 | 0
12 |  | 13 | 6 | 6 |  |  | 4 | 3 | 1 |  |  | 5 | 4 | 0
Year-1 Summary
Metric | A — Partner Joins | B — Evenings Only | C — Homeowner-Only
Total Audits
Total Self-Inspections
Total Hardening Jobs
Total Revenue ($)
Est. Year-1 Net Profit ($)
Peak Month Hours/Week
Capacity Threshold (Peak Month, hrs/wk)
Path A's threshold uses Month 12 (post-join) for comparison since that's the relevant capacity once the partner is in full-time; check earlier months against the solo rate if you want the pre-join capacity picture. Legal note: Path C drops hardening entirely, which means almost every open item in legal-risk-notes.md (contractor-licensing exemption, permits, marketing-as-contractor risk) becomes moot — there's no physical contracting work to license at all.